## CW Enhancements
ID | Type | Title | Description | Size | Suggested Priority | ACA Priority?
92351 | Enhancement | INC0159065, INC0158903: Enhance scenarios for object ownership | INC0159065, INC0158903 - Original Request: "Objects “owned” by a scenario not visible to other scenarios Description: Some situations require multiple scenarios for the same customer (branch is working PCA loans while Lending Operations is working on FLCA loans; loans may be booked at different times and be at different stages). User is unable to see which objects are “owned” by which scenario; if they inadvertently make a change in an object “owned” by another scenario, CW locks up, FPI has to script out the scenario and we start over. This typically happens on complex relationships." | XL | 1
92357 | Enhancement | Multiple Collateral Scenarios - Improved Usability or Reduce Total Allowed | Original Request: "Goal is to reduce the number of multiple collateral scenarios. It is probably infrequent that staff would want to create multiple scenarios for the same group of loans. Would like a warning if possible." FPI has been working on a design document for this. Our last discussion identified three different issues that need to be addressed: 1. Collateral Web does not notify you soon enough during the Submit process that your changes will impact another existing scenario and that you cannot continue (PRIORITY #1) 2. While you are working in one scenario, Collateral Web does not currently alert you when you have started updating a scope that is part of another existing scenario 3. Would like to be able to set a configurable limit on the number of scenarios per scope (Eastern ACA’s only) | XL | 2
92345 | Enhancement | Updating LTV ratio and LGD to the loan being booked when there is a credit action | When making a change to a scenario that will result in a credit action, update LTV and LGD for all loans in the credit action that are already getting submitted. If you are ONLY making a text change to an existing security document, or adding a UCC, this is a no-action submit, and will not result in a credit action nor an LGD/LTV update. Another possibility is that we update LTV and LGD for all loans in the scope that is impacted, but that could result in having to submit more loans than we currently do. If you are changing a description on a particular piece of collateral that is crossed with 3 loans, currently only one loan is submitted as changed to EmPOWER ("lead loan"). If we made the change, then all 3 loans would be submitted to keep the cross LGD in synch. NOTE: this is separate from the item to mass-update all LGD/LTV for that customer, which would need to be handled via a scheduled job, not inside of Collateral Web. | L | 3
80912 | Development Task | Tune: uspsvcRefreshLoanAmountsFromEmpower | This item is a development task to potentially improve performance for a database call that updates the loan amount information from EmPOWER on the Collateral Web screen. | S | 4
98698 | Enhancement | INC0202315: Smart Link Wizard for AOC in Collateral Web | Request from FCE, now that lien positioning is configured OFF in Collateral Web (as of 11/12/16 CW production release), the Smart Link Wizard for AOC when linking a collateral object (already linked to one security object) to a second security object does not need to pop up. This would also apply to Yankee. | S | 5
98721 | Enhancement | INC0198254: Collateral Analysis - change color of arrow | INC0198254, Request from Steven Rickenbacher at FCE. When opening Collateral Analysis there are only 2 loans displaying. There is a blue arrow that can be selected to improve the view. However the blue arrow is not very viable….can you see it below? It is in between these 2 columns If you push this arrow and reduce the web page you can now see all the loans which makes it much easier to view loan positions for each loan and collateral item. Is it an easy change to change the colors so this arrow is easily visible and more intuitive? **Suggest changing the color of the chevron to WHITE, so that it can show up on the blue background of the template grid. | S | 6
98716 | Enhancement | Add the ability to release UCC after loan is paid off | AgCountry & FCE request: Cannot release UCC after loan is paid off. AgCountry releases the UCC after the loan is paid off using a 1354 tran code. If there are no loans remaining open for the customer, FPI has to delete the UCC via script to remove it from the tracking report. If there are open loans, the user has to “trick” CW by linking the UCC to a different Security Agreement, then open the UCC modal and delete the UCC. | L | 7
98718 | Enhancement | Add Scenario History | Requested by FCW: History – This would be beneficial for staff to see what was completed in a previous scenario and by who. Currently the only way to do this is, is to go into Empower and try and figure out what was completed in Collateral web via Collateral Details screen. Once EmPower is replaced by EmPower Web there is a concern the forensics of a collateral problem completed by Strategy will be lost. Business need: We need to have the ability to look back through historical actions to conduct forensics in EmPower Web. Currently this is used for auditing and training purposes. If this is not preserved there will be no "why" and "how" as to what happened on a collateral error. | XL | 8
98719 | Enhancement | INC0157904 - Change process for refreshing changes to loan groups in CW after changes made in EmPOWER | Requested by AgCountry: Loan group changes not recognized in CW. CW does not appear to recognize changes to loan groups after a credit action has been linked to CW. Group errors fire in error, requiring workarounds in EmPOWER to undo the group changes, refresh CW to remove errors & submit changes, then modify the group in EmPOWER. INC0157904. May be related to 98011 (see below). Business need: Due to the business environment, we’re seeing a lot of restructuring and change in direction as RM’s work through their credit analysis. Group changes are common as guarantees are added, collateral owners changed, etc. This issue results in potential data issues, extra work, staff confusion and delayed loan closing. Any time we modify data to make something “work” we introduce risk that the data will not be corrected. When users receive these errors, they struggle, then contact the AgCountry help desk, and finally may end up with the FPI help desk before successfully booking the loan. | L | 9
98720 | Enhancement | INC0156420 - Allow building values to be adjusted using partial release functionality | Requested by AgCountry: Partial release functionality does not work for building values. Building values cannot be adjusted using partial release functionality. Business need: We don’t often take buildings, but when we need to release them we can’t use the PR functionality. | XL | 10
98722 | Enhancement | Make Collateral Web locking more like Credit Pro locking | Requested by FCE: When entering collateral web it defaults to current production. It is not until you change to a different scenario that the lock message appears. The message fades away. Request is to make the lock work more like Credit Pro. Should get the lock message as soon as you enter the customer and have user click to continue. | XL | 11
98725 | Enhancement | Real Property collateral type: the overall # of acres field should sum the # of acres field for each detail | Requested by NW: Real Property collateral type: the overall # of acres field should sum the # of acres field for each detail. Currently this does not happen and a soft error fires when validated to input the # of acres. | M | 12
98726 | Enhancement | Change Partial Release History to only count last submitted information | Requested by NW: When completing a Partial Release – if someone submits the action multiple times to EmPOWER, Collateral Web is recording the history for each submit. The collateral web should only keep the last submitted information based on when action is booked. NOTE: FPI needs more information on this item to understand what the real issue is that needs to be solved. | L | 13
98727 | Enhancement | Change color scheme in Collateral Web to be more accessible for color blind people | Requested by NW: Color scheme in Collateral Web Color scheme is difficult/impossible to see the red lines that need to be cleaned up for color blind people. | L | 14
98728 | Enhancement | Add ability to import description field from Credit Pro into Collateral Web | Requested by NW: When you import Inventory/Growing Crops (not sure of other COA) it imports the “Commodity” field into the description line in collateral web instead of the “Description” field from Credit Pro. It does import the “description” field into the comments field in web but when looking in web or the COLA you could have multiple detailed items named “wheat”. Should be winter wheat and spring wheat. Since the "Description" is an optional field, we would need to append it to the Commodity if this item were implemented. | M | 15
98729 | Enhancement | Need way to use partial release functionality to release entire real estate object | Requested by AgCountry: Not sure how to use partial release functionality to release an RE object. We create one collateral object per RE appraisal, and some mortgages are secured by multiple objects. We aren’t sure how to use the partial release functionality to track the release of an entire object, but we do need to keep track of releases so staff can easily tell that the original mortgage covers more real estate than we currently have. NOTE: FPI needs more information on this item to understand what the real issue is that needs to be solved. Partial releases are supposed to be partial, not releasing the entire object. | L | 16
98731 | Enhancement | CW requires separate credit action for Autobook functionality | Requested by AgCountry: CW requires separate credit action for Autobook functionality. AgCountry originally designated our Branch Maintenance credit action to be available for autobook. We did not want to add another action and create another “decision” about which type of action to select in CW; the user would check “autobook” if applicable. However, adding the autobook designation to Branch Maintenance seemed to affect the behavior of the branch maintenance even if we didn’t check autobook, so we had to turn the functionality off. Business need: This was a really neat feature, but we couldn’t support adding a separate credit action to be able to use the feature. Our objective was to simplify the business process, not add another decision point, so we turned it off. NOTE: FPI needs more information on this item to understand what the real issue is that needs to be solved. | L | 17
98732 | Enhancement | Need a way to signify that Autobook checkbox needs to be checked | Requested by FCW: Autobook – The checkbox is being missed by staff and actions end up not being booked in LOS. Need a way to signify that it will not be booked without the box checked (or possibly come up with a new action name that is only used for AutoBook actions that will be autobooked without a box checked). At the least, need a warning the Autobook box was not checked. Business need: The ability to Autobook feature added in for collateral remaining was an enhancement to the original collateral app. It helped to bring back the sync feature. We have quite a few open actions that result in intervening actions since these remain open. We have tried to train to check the box, yet it is forgotten by the user. There is a need for a warning that the Autobook box was not checked. Question from FPI: Are you more likely to Autobook or not to Autobook? Is this just a question of which way the checkbox is defaulted by Association? | M | 18
98733 | Enhancement | Change collateral ratios to use peak amount | Requested by FCE: Collateral ratios are not using peak amount like they should which forces users to override all-in loan amount. This shouldn't be necessary. NOTE: FPI needs more information on this item to understand more fully what we are trying to solve. | L | 19
98734 | Enhancement | Add another new column in the Quick Loan Analysis grid, called “Account Title” | Requested by NW: Add another new column in the Quick Loan Analysis grid, called “Account Title”. Simply display the Account Title that is also on each green loan icon. This makes it much easier to identify which loan is which for the user. I would place it to the right of either the existing Loan # or the Type, but we can let NW decide if this gets approved. Alternatively, if there is a configurable option to change the hyperlink blue Loan # to instead be the Account Title (not adding a new column), this would work as well. Business Need. Analysis efficiency and loan identification. The loan # is not meaningful to most users from an identification perspective, but the account title is very meaningful since July 2013. | M | 20
98735 | Enhancement | Add a new column to the Quick Loan Analysis grid on the Collateral View Display the current LGD | Requested by NW: Add a new column to the Quick Loan Analysis grid on the Collateral View Display the current LGD in a new column, to the far right, next to the L/NRV% (which is called LTV in EMPOWER LOS) that determines LGD. Make sure the LGD is displaying the “live” data from any (re)calculation that just happened in EmPOWER LOS. Business Need: All of the Collateral Analysis process with field staff is ultimately to determine the LGD on the loan. Displaying the end result of all the ratio and security analysis will put a “bow” on the Collateral package, and give insight into when the LGD may be different than what they had intended. This will increase efficiency and decrease the frequency of previously-submitted scenarios having to be touched in CW. It should also decrease a few of the Transfer Scenario instances and Technical Amendments. b. Need to Discuss: Would NW also want to add the LGD to the Calc Overview section as shown below, especially since a screen shot is taken of this and pasted into the current Credit Summary? | L | 21
98736 | Enhancement | Changes to Face Amount limitations | Requested by FCE: Example of issue: If $5,000,000 of the Face Amount was on property with an NRV of $1,000,000 and $645,000 of face amount was on property valued at $10,0000,000 the most that could be collected is $1,645,000 which is less than the combined loan amount thus it would be limited. | L | 22
98737 | Enhancement | Enhance UCC requirement error to fire for RE in cases where UCC is needed | Requested by NW: UCC Error Message The error message that says a UCC is required fires for Chattels but sometimes UCC’s are also required on RE when there are fixtures. It would be great if the error was enhanced so that if fixtures like Irrigation Equipment or Permanent Plantings were included in the RE collateral then the error would fire for those as well. Today it never fires for RE even though a UCC might actually be required. This would help ensure that UCC's are properly recorded when necessary. | M | 23
91335 | Enhancement | INC0169048 - Update Collateral mapping to pull the FCS Unit Value, not the Member Unit Value from Credit Pro | It was brought to our attention from Yankee that our Credit Pro Import is bringing in the Member Value for Unit Value, rather than the FCS value. All ACAs would need to be on board with this change as it is the same for all of them. | L | 24
98699 | Enhancement | INC0159057: All Business rules that fire on Apply Changes should also fire on Validate | In CW, there are situations in which an error message only fires when the user applies changes, but doesn't warn them when they validate their scenario. For example: Hard Error 50888 "A related scenario, ________, is already being submitted with these account(s) in common: ________. This scenario cannot be submitted." | L | 25
98011 | Enhancement | INC0160214 - Collateral Web Scenarios Can't Handle All Loan Group Relationship Changes | When a user starts an action in EmPOWER and then a scenario in Collateral Web, if the user changes the loan group in EmPOWER, they can get into trouble if the member was a collateral owner and then gets changed to a guarantor. We need to enhance EmPOWER to be aware of open Collateral Web scenarios to warn the user about changing the group, and we need to enhance Collateral Web to be aware of group changes. May be related to 98719 (see above). | L | 26
98010 | Functional Change | INC0153670/INC0157537 - Turn off User Home Screen | Originally reported issue was that the user felt that navigating to the User Home hid the workspaces but did not release the locks. The disconnect was that you are leaving Collateral Web when you go to the User Home. The screen is confusing and inconsistent with our other web applications. Our recommended solution is to move anything needed by users to the Collateral Home page, and remove the ability to navigate to User Home. | M | 27
98744 | Enhancement | Collateral Web UI should limit user entry to the max # of chars allowed | UI should limit user entry to the max # of chars allowed. This should be done for all strings in the app. Here are 4 examples: ColleteralDetailDesc = 100 chars CollateralCommentTxt = 50 chars Sec Doc / Direct Notice / Vendor name Sec Doc / Direct Notice / Vendor Address | L | 28
98012 | Enhancement | Refresh from open commitment action does not bring in all expected loans. | User is expecting to see more entities when refreshing from open commitment action, based on the web of liability. This requires more analysis about how to expand the web of liability. | XL | 29
99236 | Enhancement | Better way of linking security documents for large complex relationships | On large relationships that possess multiple commitments and multiple security documents, it can be challenging to set loan priority or edit links on new or existing loans. The “scope” feature allows a user to sort by common collateral groups to reduce the size of this “picture”, so it is easier to view, edit and maneuver. However when all of the loans are cross collateralized the scope cannot be limited and editing can prove to be very challenging. To link loans to security agreements. Create a wizard that allows users to link loans to security documents without dragging lines in “Collateral View”. This can be accomplished with a list of security documents with check boxes indicating whether the loan should be linked: Loan # Security Document 1234 2016 REM 2015 Security Agreement 2011 REM 2015 REM | L | 30
99238 | Enhancement | Would like to have a field added to the UCC screen to identify the state the UCC was filed in | Requested by FCE: Would like to have a field added to the UCC screen to identify the state the UCC was filed in. This could help to ensure that filing requirements are met for those states that require additional language, etc. (such as NJ). | M | 31

## CW Defects
ID | Title | Description | Suggested Priority | ACA Priority?
85161 | Collateral Owner - submitting collateral with attributes can create collateral components with 2 lead owners | If collateral is submitted in a certain scenario, you can end up with collateral components with two different lead owners. This causes problems and requires a data cleanup in order to proceed. This happens frequently and is a high priority to fix. | 1 | 2
81239 | Irrigation is missing Required Field but shows as Green Completed (rule catches problem) | The UI incorrectly shows the Irrigation panel as Green even though it is missing a required field. On a good note, the BR rule catches the missing field and throws soft error that the Irrigation panel is required/missing. | 2 | 2
82439 | (Chrome Only) Application error when linking new loan in Collateral Web | This issue only occurs in the Chrome browser. If linking a new loan in Chrome, the user will get an unexpected error. | 3 | 2
82908 | Scenarios are not locked down while submitting. Scenario stays in "Open" status in DB and is R/W | While a scenario is in process of submitting and after it has submit errors for review, it is possible to open it and make changes. This should be fixed. | 4 | 2
83752 | INC0158937 - Collateral WEB not reflecting correct collateral | Noticed that Collateral WEB has incorrect current collateral information for customer Chad Rava Living Trust. A new loan was booked for this customer (8334196), on 03/07/16 with an LTV of 49.70%. Empower appears to be correct in reflecting this information, but Collateral WEB does not. The piece of collateral "Hwy 41 192.6 ac." now has a $0 balance in WEB, when it was booked yesterday with a value of $7,310,000. From INCIDENT: Some research was done and we found that the collateral in question had a single detail row that was deleted. When that delete happened, the values copied up to the summary level component, however the record was not tagged as updated, and was not included in the Collateral Submit to EmPOWER. All the calculations in Web were based off the correct amount, but this is why the RE shows $0 in Current Production. Currently researching exactly what happened and a fix, however in the meantime, workaround is to go in, add the correct MV back to the top panel, and re-submit back to EmPOWER. | 5 | 4
84142 | SQL 2014 Performance: Rewrite uspsvcRetrieveLoanSummary to remove with cardinality trace flag | We upgraded the database version late 2016, and some of the code performs differently in the new version. This item is to help with performance and will hopefully speed up the process of loading the screen. | 6 | 4
81120 | INC0141516/INC0181722/INC0180597 - Update Error When Multiple Versions of Group to be more user friendly | When a user links multiple open EmPOWER actions with two versions of the same group, there should be a user error, but currently the error is confusing and hard to read. The error should be updated to be make more sense to the end user. | 7 | 2
85236 | INC0155337/INC0164143 - Unable to get property 'securityDocumentTypeCde' of undefined or null reference | Error when trying to open Emery J Byler. Tried opening the customer yesterday and let it try and load for 10 or so minutes but it never came up. Able to work in other customers without error. | 8 | 4
86748 | INC0167262 - UCC does not have same list of possible owners | The same UCC object was being set up so that one was a UCC and one was an EFS. The one for the UCC showed 4 possible collateral owners but the one for the EFS only showed 3. We were not able to mark one of the owners because of this. | 9 | 3
88932 | INC0176644 - Unexpected SQL error occurred in uspInserttblSecurityCollateralClause (#2627). Violation of PRIMARY KEY constraint 'PK_tblSecurityCollateralClause' | User ended up in a state where it tried to insert the same security agreement twice. Got a hard error. | 10 | 4
88526 | INC0175073 - Cannot Right Click on relationship line in CV after modifying Lien/Loan Position and hitting [Enter] | If the user closes the Modify Relationship modal by using the ENTER key, the relationship line cannot be right-clicked. Clicking an object to get a menu or pin will fix the problem as a workaround, but it would be good to fix this. | 11 | 3
88310 | INC0175186 - FK Error BECSecurityDocument.tblDocument on SecurityDocument delete | User received a hard error when trying to delete security documents. Required a data cleanup by FPI to fix. This item is to fix the root cause. | 12 | 4
92105 | INC0184864 - Multiple UCC Owners cannot be deleted successfully | Currently Collateral Web throws errors on Submit when multiple UCC Owners exist for a UCC. In most cases the owners are marked for deletion and the workaround is to run an adhoc script to delete the owners from Empower and then mark those records as deleted/processed in the Scenario. This should be research as to why it fails on submit. | 13 | 4
93766 | INC0190836 - Summary Collateral Row Not Updated and Submitted Back to EmPOWER When Single Detail Row is Removed | If a piece has one single detail row that is deleted and no other changes are made, the summary row is not re-submitted, which will cause the value to be incorrect. | 14 | 2
86754 | INC0168356 - Lexington Collateral Issue - why did collateral changes in scope 1 impact loans in scope 2 | We had a case come in from Steve where a loan was submitted in Scenario 1 with new loan positions, and the same loan came in as updated in Scenario 2, even though it wasn't edited. I believe it's due to the baseline correction we do when we create the scenario. The loan positions were in our relationship table, but not in baseline. When we created the scenario, we saw the difference, and correct the loan positions to match the EmPOWER baseline, which set them back to 1. | 15 | 3
87846 | AgC/Yankee: Update Role access (tblSecProfileProcessActivityAccessOverride) to lock down CollateralWeb app. | During the Collateral Remaining Rollout in 2015 some additional cleanup to the lockdown configs were discovered. tblSecProfileProcessActivityAccessOverride clean-up. Some profiles got "Full Access" configs when they should have gotten Read-Only Access based on pre-Collateral Config decisions. | 16 | 4
87959 | INC0173022 - Error fires even though Irrigation and Water Rights are present | The user reported an issue that the Irrigation and Water Rights soft error was firing even though the Irrigation and Water Rights were present and all panels were green. | 17 | 4
89504 | INC0178497 - Loading Scenario Screen keeps spinning displaying "Formatting for display" and user receives Application Error: Unable to get property 'securityDocumentOID' of undefined or null reference | User getting an error message when opening Collateral Web from a Full Renewal LOS action. When they try to close out of the error message his screen keeps spinning and displaying "Formatting data for display". Application Error: Unable to get property 'securityDocumentOID' of undefined or null reference on line #1 from https://empower.farmcrediteast.com/Bundles/CollateralJS? v=yjzl7UBcsLCN5xG6_AfWIKA7D2EWipFGqfuXPGXJOFl1 | 18 | 4
90697 | INC0180753 Hard Error SecurityDocumentSaveEmpower() uspsvcInserttblSecurityCommitmentJoin ABORT ON ERROR | Summary: User was trying to change the date on a mortgage and received an error about Unexpected SQL error occurred in uspsvcInserttblSecurityCommitmentJoin. | 19 | 3
91917 | INC0184213 - uspsvcInserttblSecurityAgreementCollateralJoin Error PK_tblSecurityAgreementCollateralJoin | Summary: a user made several changes (details unknown) and received an Unexpected SQL Error about security documents. | 20 | 3
92727 | INC0186965 - Scenario is Awaiting Nightly Cycle when it should be a Candidate for Transfer | There exists a situation when you have multiple linked commitments and you process some in EmPOWER before processing the Collateral Web scenario, the scenario should be Candidate for Transfer but is instead Awaiting Nightly Cycle. | 21 | 4
93933 | INC0191511 - Incorrect error when transferring a scenario | When trying to transfer a scenario, we received an error saying that it was in 'Submitted' status. I can say 100% that it was listed as 'Candidate for Transfer' when we opened the scenarios dropdown, and the scenario was read only for that matter. It still opened the scenario up for editing, but it did not change the name to 'Transferred from...'. After 'transferring' the scenario listed as 'Submitted' and let us continue working. We received an error that said, "ScenarioID = 3204 is in a state of 'Submitted', which is not a candidate for transfer. [Transfer Scenario]' | 22 | 4
97296 | Submit rule is not warning that owner panel for the summary row is required/missing | There isn't an owner data entered for the summary collateral. The data wizard correctly shows the panel as orange (required/missing). I expected to get a validation error on the validate and/or submit that this collateral was missing required owner data... but don't. This seems to work fine if the detail collateral is missing owners... just not the summary. | 23 | 4
97475 | Apply Changes - Autobook now checkbox isn't always visible when credit action that has autobook capability is selected | If changing the credit action type on the Apply Changes to EmPOWER screen to a type where "Autobook now" isn't applicable, and then submitting so that a hard error is generated, if you re-open the Apply Changes screen and change the credit action type back to one that should have "Autobook now", the checkbox is not displayed. | 24 | 4
98746 | Collateral Web - add foreign keys to import tracking tables | This item is to fortify the application to prevent bad data from being created in the database. | 25 | 4